## Product Roadmap
Instructions: Based on the scenario, place the Product Features into the phases on the Product Roadmap. The product features should be orderd so that the highest value features are delivered to users first and the simple to implement features are delivered before the more complex features. The product Features are listed in Column A. Each Cell in the four phases of the Product Roadmap has a dropdown list that allows you to select the product features that you want to appear in that phase of the roadmap. Every feature must be added to a Phase of the roadmap.
Product Feature List | Phase 1 | Phase 2 | Phase 3 | Phase 4
Initial Architecture/Database Setup & Design | Initial Architecture/Database Setup & Design
Develop iOS Compatible Mobile App |  | Develop iOS Compatible Mobile App
Develop Android Compatible Mobile App |  |  | Develop Android Compatible Mobile App
Develop Web Portal application | Develop Web Portal application
Upgrade Database |  |  |  | Upgrade Database
Security Update |  | Security Update
Manual Importing | Manual Importing
Automated Integration for Importing |  |  | Automated Integration for Importing
Mobile App User Interface Refinement |  |  |  | Mobile App User Interface Refinement
Authentication- Login/Logout | Authentication- Login/Logout
Basic Dashboard with heatmap display | Basic Dashboard with heatmap display
Basic Data Searching Capability | Basic Data Searching Capability
Automated Amber Alerts |  | Automated Amber Alerts
Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities |  |  | Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities
User Based Preferences- Save Search & Reports |  | User Based Preferences- Save Search & Reports
Web Portal Redesign |  |  |  | Web Portal Redesign
Export CSV of Reported Data |  |  |  | Export CSV of Reported Data
Send Manual Amber Alerts by Region | Send Manual Amber Alerts by Region
Web Report of Data (View only no Export) | Web Report of Data (View only no Export)
In-App messaging for Doctors and Patients |  |  |  | In-App messaging for Doctors and Patients

## User Roles
Instructions: Below are 7 user roles that have been identified for the product and a brief description for how each user will interact with the product. These user roles can be used to create user stories in the blue "User Story" tab.
Roles | Personas
CDC Officials | Will use product to determine where to apply funding and send test kits
System Administrators | Responsible for governing all roles of the product. This role is not a health professional. This role maintains and governs the system, the process, and does troubleshooting if other users have problems with their roles and access. This role also publishes product information and ensures that the system is performing as intended.
Patients | Will use the product to report, track, and monitor cases of the outbreak
Test Centers | Will use the product to report test kit usage
Doctors | Will use the product to share successful treatment remedies
Medical Examiners | Will use the product to report deaths caused by outbreak
Healthcare Companies | Will use the product to report test kit production and deliveries

## User Stories
Instructions: Create User Stories and Acceptance Criteria in the sheet using the 7 user roles that have been identified in the yellow user role tab. Two user stories have been provided for you for each role. Create at least 2 more user stories for each role based on the needs of each user. You will have at least 28 total user stories when finished. List at least 2 acceptance criteria for each User Story
As a.. | ....I can... | ...so that... | Completed User Story | Acceptance Criteria (Minimum of 2)
CDC Official | view the number of patients that have reported testing positive | I can analyze the outbreak | As a CDC Official I can view the number of patients that have reported testing positive so that I can analyze the outbreak . | - Patient names are anonymous - User can see a summary of the numbers provided - User must be logged in from a government IP address to view
CDC Official | see a report of the # of test kits that health care companies have created | I can send funding | As a CDC Official I can see a report of the # of test kits that health care companies have created so that I can send funding. | - User can see a summary of the total number of test kits - User can see a summary of the number of test kits produced by healthcare company - User can see the names of the health care company - User can see amount of funds sent to each health care company
CDC Official | set up alerts for new outbreaks in specific regions | quickly respond to new outbreaks and allocate resources to those regions | As a CDC Official I can set up alerts for new outbreaks in specific regions so that quickly respond to new outbreaks and allocate resources to those regions. | - The system must allow CDC Officials to set up alerts for new outbreaks in specific regions. - The alerts should be triggered when a certain number of cases are reported in a specific region. - CDC Officials should be able to define the threshold for the number of cases that should trigger the alert. - The alerts should be sent to CDC Officials via email. - The alerts should contain information about the outbreak, including the number of cases, the location, and any other relevant information. - CDC Officials should be able to specify the regions for which they want to receive alerts. - The system should allow CDC Officials to modify or cancel alerts at any time. - The system should be able to generate reports on the number of alerts that have been triggered, and the actions that have been taken in response to those alerts.
CDC Official | view the progress of vaccine and cure development for the virus | plan for future outbreaks and make informed decisions about funding allocation | As a CDC Official I can view the progress of vaccine and cure development for the virus so that plan for future outbreaks and make informed decisions about funding allocation. | - The system should provide a dashboard that displays the progress of vaccine and cure development for the virus in real-time. - The dashboard should show the current stage of development, including any clinical trials or testing. - The dashboard should display the estimated time frame for completion of each stage of development. - The dashboard should show the success rate and effectiveness of any vaccine or cure that is in development. - The dashboard should allow CDC officials to compare and contrast the progress of different vaccines or cures being developed. - The dashboard should allow CDC officials to filter the information by various criteria such as the region, the company developing the vaccine, or the type of vaccine being developed. - The information displayed on the dashboard should be regularly updated, with the latest information about the progress of vaccine and cure development. - The dashboard should be accessible only to authorized CDC officials and should maintain confidentiality and security of the information displayed.
Doctor | change my test results | I can add treatments | As a Doctor I can change my test results so that I can add treatments . | - Alpha Numeric characters are allowed - Patient First and Last Name required - Patient DOB required - Patient Location Required - Patient Gender is optional
Doctor | login to the system | I can enter patient treatment information | As a Doctor I can login to the system so that I can enter patient treatment information. | - User name and email address required - User is locked out after 3 incorrect entries
Doctor | search for patient information by name or ID number | I can easily access their medical history and make informed treatment decisions | As a Doctor I can search for patient information by name or ID number so that I can easily access their medical history and make informed treatment decisions. | - The search function should be able to search by patient name or ID number - The search results should display relevant patient information, including medical history and previous treatments - The search function should be fast and reliable - The search function should only display information for patients the doctor is authorized to view.
Doctor | view real-time updates on the number of new cases and deaths related to the virus | stay informed about the current state of the outbreak | As a Doctor I can view real-time updates on the number of new cases and deaths related to the virus so that stay informed about the current state of the outbreak. | - The real-time updates should be accurate and up-to-date - The updates should display the number of new cases and deaths for the current day, as well as a cumulative total - The updates should be displayed in an easily accessible location, such as a dashboard or notification system - The updates should include information about the location and demographics of new cases, if available.
Healthcare Company | add the number of test kits produced | the CDC can determine where test kits should be sent | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | - only numeric characters allowed - User can see data that previously entered
Healthcare Company | reset my password by myself | I can login again. | As a Healthcare Company I can reset my password by myself so that I can login again. . | - User must verify email address - User must verify answer security question to reset password
Healthcare Company | view the current inventory of raw materials needed for producing test kits | I can plan my future production and ensure timely delivery | As a Healthcare Company I can view the current inventory of raw materials needed for producing test kits so that I can plan my future production and ensure timely delivery. | - The system should provide real-time data on the current inventory of raw materials. - The system should have an option to update the inventory once new raw materials are received. - The system should have a feature to set a threshold level of inventory to alert the healthcare company to restock raw materials.
Healthcare Company | generate reports on test kit production and delivery for a specific period | I can track my performance and analyze areas of improvement | As a Healthcare Company I can generate reports on test kit production and delivery for a specific period so that I can track my performance and analyze areas of improvement. | - The system should have an option to generate customized reports based on user-selected parameters such as date range, production units, and delivery locations. - The system should provide visual representations of data such as charts and graphs. - The system should allow users to export reports in various formats such as Excel or PDF.
Medical Examiner | add a person's gender | deaths can be tracked by gender | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | - User can select from list of genders - User can update gender selection - Users gender selection is not shared with CDC Officials
Medical Examiner | am automatically logged out of the system | no one can access my account | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | - Timeout occurs after 15 mins of inactivity - After timeout user is returned to login page
Medical Examiner | view a summary of deaths caused by the outbreak sorted by region | quickly identify which regions are being hit the hardest | As a Medical Examiner I view a summary of deaths caused by the outbreak sorted by region so that quickly identify which regions are being hit the hardest. | - The summary of deaths includes the number of deaths by region - The summary is sorted in descending order by number of deaths - The summary is easily accessible from the Medical Examiner dashboard
Medical Examiner | search for a specific death report by name or other identifying information | quickly access and review the report | As a Medical Examiner I search for a specific death report by name or other identifying information so that quickly access and review the report. | - The search function allows the Medical Examiner to search by name or other identifying information - The search function returns relevant death reports - The relevant death report is easily accessible from the search results
Patient | change my test results | the system data is accurate | As a Patient I can change my test results so that the system data is accurate. | - User can modify test results twice - Doctors are notified when a patient changes test results
Patient | enter any stores that I visited 3 days before testing positive | others are aware of their potential exposure to the virus | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | - Option only visible for patients that report positve test - Can specify store name, date entered, city, and state
Patient | view the status of my test results | take appropriate actions based on the results | As a Patient I can view the status of my test results so that take appropriate actions based on the results. | - The patient can see if their test results are positive, negative, or pending. - If the results are positive, the patient will be prompted to enter any stores or people they had contact with. - If the results are pending, the patient will be notified when the results are available.
Patient | view a heat map of outbreak areas | take precautions and avoid potential hotspots | As a Patient I can view a heat map of outbreak areas so that take precautions and avoid potential hotspots. | - The heat map is interactive and can be zoomed in and out. - The heat map is updated in real-time based on the latest data from the CDC. - The heat map shows the severity of outbreaks in different regions using different colors or shading. - The heat map is accessible through the patient's account dashboard.
System Administrator | give access to the system | users can access,import, share data. | As a System Administrator I can give access to the system so that users can access,import, share data.. | - First and Last Name required - Enter email addresses - Gmail email address are not allowed access
System Administrator | remove access | users are not able to access the system | As a System Administrator I can remove access so that users are not able to access the system. | - Removed user recieves email confirmation of removal - Removed user can't login once removed - System administrator must confirm the user that they are removing before leaving the page
System Administrator | monitor system logs for any errors or issues | quickly resolve them and prevent any potential downtime or data loss | As a System Administrator I can monitor system logs for any errors or issues so that quickly resolve them and prevent any potential downtime or data loss. | - The system logs are easily accessible and provide detailed information about errors and issues. - The System Administrator is notified in real-time when an error or issue is detected. - The System Administrator can quickly and easily identify the root cause of the error or issue and take appropriate action to resolve it. - The System Administrator can track the status of each issue and verify that it has been resolved.
System Administrator | configure system settings to optimize performance | users access and use the system quickly and efficiently | As a System Administrator I can configure system settings to optimize performance so that users access and use the system quickly and efficiently. | - The System Administrator can easily access and modify system settings. - The System Administrator can configure settings related to server performance, database optimization, and network bandwidth. - The System Administrator can test the system performance before and after making changes to verify the effectiveness of the configuration changes. - The System Administrator can monitor system performance after making changes to ensure that the system is operating optimally.
Test Center | update/change the number of test kits recieved | data is accurate | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | - Only allow update one time - Make user confirm change before leaving the page
Test Center | I want to be notified when my stock falls before a certain level, | I can proactively order additional testing supplies | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | - System notifies user by email - User can set number that stock must reach for email to be sent - System notifies user upon login that stock is low
Test Center | track the number of positive cases detected through our testing | report accurate statistics to public health agencies and make data-driven decisions about testing strategies | As a Test Center I can track the number of positive cases detected through our testing so that report accurate statistics to public health agencies and make data-driven decisions about testing strategies. | - The system must allow Test Centers to input the number of positive cases detected through their testing. - The system must automatically calculate the positivity rate based on the number of positive cases and total tests performed. - The system must allow Test Centers to view and export data on positivity rates over time.
Test Center | schedule appointments for patients to be tested | testing can be efficiently managed and wait times are minimized | As a Test Center I can schedule appointments for patients to be tested so that testing can be efficiently managed and wait times are minimized. | - The system must allow Test Centers to create appointments for patients to be tested. - Patients must be able to select available appointment slots online. - The system must send confirmation and reminder emails to patients and Test Center staff. - The system must allow Test Centers to view and manage their appointment schedule.

## Priority
Instructions: All of the user stories that you created will automatically appear in this sheet. Prioritize the user stories so that the highest value features are delivered to users first using the following parameters: There are 3 Releases- Release 1-MVP, Release 2, and Release 3 (All contained in the dropdown menus in Column D) - Release 1 (MVP) contains 3 sprints. The release can only have 10 user stories within the 3 sprints - Sprint 1 will have 3 user stories - Sprint 2 will have 4 user stories - Sprint 3 will have 3 user stories - Release 2 contains 2 sprints. The release can only have 10 user stories within the 2 sprints - Sprint 4 and Sprint 5 will each have 5 user stories - Release 3 contains 2 sprints. The release can only have 5 user stories within the 2 sprints - Sprint 6 will have 2 user stories - Sprint 7 will have 3 user stories - All remaining user stories are assigned to "Backlog for Future Release" - Assign the sprint that the user stories will be in within that particular release in Column E. If it is is "Backlog for Future Release" the user story doesn't need to be assigned a sprint. |  |  |  |  | Hints/Tips: - Question if a user role has too much functionality to be in the MVP release. - Question what is a nice-to-have vs high-value based on the scenario and vision. - Question if you should trade off- what is the worst thing that could happen if the user had to wait for that functionality to come later. - Refine, rewrite, or delete a user story in the blue user story tab if it doesn’t fit into your Release or MVP plan
Role | User Story | Acceptance Critieria | Release | Sprint | Sprint | Release 1-MVP Total Stories =10 | Release 2 Total Stories =10 | Release 3 Total Stories =5 | Backlog for Future Release
CDC Official | As a CDC Official I can view the number of patients that have reported testing positive so that I can analyze the outbreak . | - Patient names are anonymous - User can see a summary of the numbers provided - User must be logged in from a government IP address to view | Release 1 (MVP) | 1 | 1 Total Stories = 3 | 3
CDC Official | As a CDC Official I can see a report of the # of test kits that health care companies have created so that I can send funding. | - User can see a summary of the total number of test kits - User can see a summary of the number of test kits produced by healthcare company - User can see the names of the health care company - User can see amount of funds sent to each health care company | Release 1 (MVP) | 3 | 2 Total Stories = 4 | 4
CDC Official | As a CDC Official I can view the progress of vaccine and cure development for the virus so that plan for future outbreaks and make informed decisions about funding allocation. | - The system should provide a dashboard that displays the progress of vaccine and cure development for the virus in real-time. - The dashboard should show the current stage of development, including any clinical trials or testing. - The dashboard should display the estimated time frame for completion of each stage of development. - The dashboard should show the success rate and effectiveness of any vaccine or cure that is in development. - The dashboard should allow CDC officials to compare and contrast the progress of different vaccines or cures being developed. - The dashboard should allow CDC officials to filter the information by various criteria such as the region, the company developing the vaccine, or the type of vaccine being developed. - The information displayed on the dashboard should be regularly updated, with the latest information about the progress of vaccine and cure development. - The dashboard should be accessible only to authorized CDC officials and should maintain confidentiality and security of the information displayed. | Release 1 (MVP) | 3 | 3 Total Stories = 3 | 3
CDC Official | As a CDC Official I can set up alerts for new outbreaks in specific regions so that quickly respond to new outbreaks and allocate resources to those regions. | - The system must allow CDC Officials to set up alerts for new outbreaks in specific regions. - The alerts should be triggered when a certain number of cases are reported in a specific region. - CDC Officials should be able to define the threshold for the number of cases that should trigger the alert. - The alerts should be sent to CDC Officials via email. - The alerts should contain information about the outbreak, including the number of cases, the location, and any other relevant information. - CDC Officials should be able to specify the regions for which they want to receive alerts. - The system should allow CDC Officials to modify or cancel alerts at any time. - The system should be able to generate reports on the number of alerts that have been triggered, and the actions that have been taken in response to those alerts. | Release 1 (MVP) | 2 | 4 Total Stories = 5 |  | 5
Healthcare Company | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | - only numeric characters allowed - User can see data that previously entered | Release 1 (MVP) | 2 | 5 Total Stories = 5 |  | 5
Healthcare Company | As a Healthcare Company I can view the current inventory of raw materials needed for producing test kits so that I can plan my future production and ensure timely delivery. | - The system should provide real-time data on the current inventory of raw materials. - The system should have an option to update the inventory once new raw materials are received. - The system should have a feature to set a threshold level of inventory to alert the healthcare company to restock raw materials. | Release 1 (MVP) | 2 | 6 Total Stories = 2 |  |  | 2
Medical Examiner | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | - Timeout occurs after 15 mins of inactivity - After timeout user is returned to login page | Release 1 (MVP) | 2 | 7 Total Stories = 3 |  |  | 3
System Administrator | As a System Administrator I can give access to the system so that users can access,import, share data.. | - First and Last Name required - Enter email addresses - Gmail email address are not allowed access | Release 1 (MVP) | 1 | Sum | 10 | 10 | 5
System Administrator | As a System Administrator I can remove access so that users are not able to access the system. | - Removed user recieves email confirmation of removal - Removed user can't login once removed - System administrator must confirm the user that they are removing before leaving the page | Release 1 (MVP) | 1 | Total | 10 | 10 | 5 | 3
Test Center | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | - Only allow update one time - Make user confirm change before leaving the page | Release 1 (MVP) | 3 | SUM = TOTAL | #NAME? | #NAME? | #NAME?
Doctor | As a Doctor I can login to the system so that I can enter patient treatment information. | - User name and email address required - User is locked out after 3 incorrect entries | Release 2 | 4
Healthcare Company | As a Healthcare Company I can reset my password by myself so that I can login again. . | - User must verify email address - User must verify answer security question to reset password | Release 2 | 4
Medical Examiner | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | - User can select from list of genders - User can update gender selection - Users gender selection is not shared with CDC Officials | Release 2 | 4
Medical Examiner | As a Medical Examiner I view a summary of deaths caused by the outbreak sorted by region so that quickly identify which regions are being hit the hardest. | - The summary of deaths includes the number of deaths by region - The summary is sorted in descending order by number of deaths - The summary is easily accessible from the Medical Examiner dashboard | Release 2 | 4
Medical Examiner | As a Medical Examiner I search for a specific death report by name or other identifying information so that quickly access and review the report. | - The search function allows the Medical Examiner to search by name or other identifying information - The search function returns relevant death reports - The relevant death report is easily accessible from the search results | Release 2 | 4
Doctor | As a Doctor I can change my test results so that I can add treatments . | - Alpha Numeric characters are allowed - Patient First and Last Name required - Patient DOB required - Patient Location Required - Patient Gender is optional | Release 2 | 5
Doctor | As a Doctor I can search for patient information by name or ID number so that I can easily access their medical history and make informed treatment decisions. | - The search function should be able to search by patient name or ID number - The search results should display relevant patient information, including medical history and previous treatments - The search function should be fast and reliable - The search function should only display information for patients the doctor is authorized to view. | Release 2 | 5
Healthcare Company | As a Healthcare Company I can generate reports on test kit production and delivery for a specific period so that I can track my performance and analyze areas of improvement. | - The system should have an option to generate customized reports based on user-selected parameters such as date range, production units, and delivery locations. - The system should provide visual representations of data such as charts and graphs. - The system should allow users to export reports in various formats such as Excel or PDF. | Release 2 | 5
Patient | As a Patient I can change my test results so that the system data is accurate. | - User can modify test results twice - Doctors are notified when a patient changes test results | Release 2 | 5
System Administrator | As a System Administrator I can configure system settings to optimize performance so that users access and use the system quickly and efficiently. | - The System Administrator can easily access and modify system settings. - The System Administrator can configure settings related to server performance, database optimization, and network bandwidth. - The System Administrator can test the system performance before and after making changes to verify the effectiveness of the configuration changes. - The System Administrator can monitor system performance after making changes to ensure that the system is operating optimally. | Release 2 | 5
Doctor | As a Doctor I can view real-time updates on the number of new cases and deaths related to the virus so that stay informed about the current state of the outbreak. | - The real-time updates should be accurate and up-to-date - The updates should display the number of new cases and deaths for the current day, as well as a cumulative total - The updates should be displayed in an easily accessible location, such as a dashboard or notification system - The updates should include information about the location and demographics of new cases, if available. | Release 3 | 6
Patient | As a Patient I can view the status of my test results so that take appropriate actions based on the results. | - The patient can see if their test results are positive, negative, or pending. - If the results are positive, the patient will be prompted to enter any stores or people they had contact with. - If the results are pending, the patient will be notified when the results are available. | Release 3 | 6
System Administrator | As a System Administrator I can monitor system logs for any errors or issues so that quickly resolve them and prevent any potential downtime or data loss. | - The system logs are easily accessible and provide detailed information about errors and issues. - The System Administrator is notified in real-time when an error or issue is detected. - The System Administrator can quickly and easily identify the root cause of the error or issue and take appropriate action to resolve it. - The System Administrator can track the status of each issue and verify that it has been resolved. | Release 3 | 7
Test Center | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | - System notifies user by email - User can set number that stock must reach for email to be sent - System notifies user upon login that stock is low | Release 3 | 7
Test Center | As a Test Center I can track the number of positive cases detected through our testing so that report accurate statistics to public health agencies and make data-driven decisions about testing strategies. | - The system must allow Test Centers to input the number of positive cases detected through their testing. - The system must automatically calculate the positivity rate based on the number of positive cases and total tests performed. - The system must allow Test Centers to view and export data on positivity rates over time. | Release 3 | 7
Patient | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | - Option only visible for patients that report positve test - Can specify store name, date entered, city, and state | Backlog for Future Release | N/A
Patient | As a Patient I can view a heat map of outbreak areas so that take precautions and avoid potential hotspots. | - The heat map is interactive and can be zoomed in and out. - The heat map is updated in real-time based on the latest data from the CDC. - The heat map shows the severity of outbreaks in different regions using different colors or shading. - The heat map is accessible through the patient's account dashboard. | Backlog for Future Release | N/A
Test Center | As a Test Center I can schedule appointments for patients to be tested so that testing can be efficiently managed and wait times are minimized. | - The system must allow Test Centers to create appointments for patients to be tested. - Patients must be able to select available appointment slots online. - The system must send confirmation and reminder emails to patients and Test Center staff. - The system must allow Test Centers to view and manage their appointment schedule. | Backlog for Future Release | N/A

## Release Plan & MVP Plan
Instructions: Create a Release & MVP Plan in this sheet. Copy your 10 Release 1 (MVP) user stories from Priority sheet into column C, Rows 3-12 below in the appropriate sprint. Copy your 10 Release 2 user stories from Priority sheet into column C, Rows 13-22 below in the appropriate sprint. Copy your 5 Release 3 user stories from Priority sheet into column C, Rows 23-27 below in the appropriate sprint.
Releases | Sprints | User Story | Story Points
Release 1- MVP | Sprint 1 | As a System Administrator I can give access to the system so that users can access,import, share data.. | 2
|  | As a System Administrator I can remove access so that users are not able to access the system. | 3
|  | As a CDC Official I can view the number of patients that have reported testing positive so that I can analyze the outbreak . | 3
| Sprint 2 | As a CDC Official I can set up alerts for new outbreaks in specific regions so that quickly respond to new outbreaks and allocate resources to those regions. | 5
|  | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | 0.5
|  | As a Healthcare Company I can view the current inventory of raw materials needed for producing test kits so that I can plan my future production and ensure timely delivery. | 2
|  | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | 0.5
| Sprint 3 | As a CDC Official I can view the progress of vaccine and cure development for the virus so that plan for future outbreaks and make informed decisions about funding allocation. | 5
|  | As a CDC Official I can see a report of the # of test kits that health care companies have created so that I can send funding. | 2
|  | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | 1
Release 2 | Sprint 4 | As a Doctor I can login to the system so that I can enter patient treatment information. | 5
|  | As a Healthcare Company I can reset my password by myself so that I can login again. . | 0.5
|  | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | 1
|  | As a Medical Examiner I view a summary of deaths caused by the outbreak sorted by region so that quickly identify which regions are being hit the hardest. | 1
|  | As a Medical Examiner I search for a specific death report by name or other identifying information so that quickly access and review the report. | 0.5
| Sprint 5 | As a Doctor I can change my test results so that I can add treatments . | 1
|  | As a Doctor I can search for patient information by name or ID number so that I can easily access their medical history and make informed treatment decisions. | 2
|  | As a Healthcare Company I can generate reports on test kit production and delivery for a specific period so that I can track my performance and analyze areas of improvement. | 2
|  | As a Patient I can change my test results so that the system data is accurate. | 1
|  | As a System Administrator I can configure system settings to optimize performance so that users access and use the system quickly and efficiently. | 3
Release 3 | Sprint 6 | As a Doctor I can view real-time updates on the number of new cases and deaths related to the virus so that stay informed about the current state of the outbreak. | 3
|  | As a Patient I can view the status of my test results so that take appropriate actions based on the results. | 5
| Sprint 7 | As a System Administrator I can monitor system logs for any errors or issues so that quickly resolve them and prevent any potential downtime or data loss. | 2
|  | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | 0.5
|  | As a Test Center I can track the number of positive cases detected through our testing so that report accurate statistics to public health agencies and make data-driven decisions about testing strategies. | 5